## Testing Status
Testing Status Report
SL-CMMI-T-TSR
Project Status
|  | Project Name: | EdgeAX Commercelink Vitamin World Implementation Phase II
SL PM:
|  | Module | All
|  | Report Date | 2016-05-08
|  | Current Cycle | Cycle 2
|  | Total Planned Days for Current Cycle | 10
|  | Planned Completion Date of Current Cycle | 2017-05-08
|  | Planned Execution Till Today | 65%
|  | Actual Execution Till Today | 60%
|  | Remaining Execution | 39.57%
Functionality wise Execution Status
Sr. | Functionality | Components | % Weight | % Execution for Functionality | % Execution for Release | Comments
1 | Sales Order | Ecom to AX-Basic Flows | 15% | 60% | 9%
|  | Shipping Charges & Tax Charges | 5% | 25% | 1.25%
|  | Discount & Promotions & Rebate Implementation | 27% | 7.9% | 2.133%
|  | Sales Order Status | 3% | 0% | 0%
2 | Catalog | Catalog, Product[Custom attributes and Product Images] | 10% | 89% | 8.9%
3 | Pricing | Pricing | 10% | 99% | 9.9%
4 | Discounts | Periodic Discounts | 25% | 98% | 24.5%
5 | Inventory | Inventory | 5% | 95% | 4.75%
|  |  |  | Total Execution | 60.43%
Description :
% weight will be assigned considering the effort/time to execute related test cases
% Execution for Functionality shows test case execution % for that particular functionality
% Execution for Release shows over all test case execution. Formula to calculate is (% weight * % execution for Functionality) / 100
Other Consideration
Sr. | Description
1 | 10 defects are closed today, 5 defects are active. 2 defect are resolved state.
2 | Pending Resolved Issues Verification will be done when sales order testing starts. Main focus is on 'Merchandizing' now.
3
4
5
Note on E14: Auto Calculated
Note on E15: Auto Calculated

## Defects Sheet
Defects Status as of date
Sr. | Testing Date | Testing Day Number | # of Test Cases Executed (Incremental) | Defect Severity | In-Progress Statuses |  | Closed Statuses | Totals |  |  |  |  | Total | Defects Ratio | Projected Defects | Daily Defect Closed Count | Defect Detection Ratio | System Testing Productivity (testcase / manhour) | Incorrect Defect Reporting %
[5 empty] | Active | Resolved | Closed | Critical Total | High Total | Medium Total | In-Progress Total | Closed Total
1 | 2016-04-14 | 2 |  | Critical |  |  | 1 | 1 | 10 | 4 | 10 | 5
|  |  |  | High | 7 | 1 | 2
|  |  |  | Medium | 2 |  | 2
2 | 2016-04-15 | 3 |  | Critical |  |  | 1 | 1 | 2 | 2 | 0 | 5
|  |  |  | High |  |  | 2
|  |  |  | Medium |  |  | 2
3 | 2016-04-20 | 8 |  | Critical |  |  | 3 | 3 | 4 | 3 | 0 | 10
|  |  |  | High |  |  | 4
|  |  |  | Medium |  |  | 3
4 | 2016-04-21 | 9 |  | Critical |  |  | 2 | 2 | 7 | 6 | 0 | 15
|  |  |  | High |  |  | 7
|  |  |  | Medium |  |  | 6
5 | 2016-04-22 | 10 |  | Critical | 1 |  | 1 | 2 | 12 | 11 | 17 | 8
|  |  |  | High | 6 | 4 | 2
|  |  |  | Medium | 2 | 4 | 5
6 | 2017-04-28 | 18 |  | Critical |  |  | 1 | 1 | 3 | 0 | 0 | 4
|  |  |  | High |  |  | 3
Medium
7 | 2017-05-03 | 23 |  | Critical |  |  | 2 | 2 | 2 | 6 | 0 | 10
|  |  |  | High |  |  | 2
|  |  |  | Medium |  |  | 6
8 | 2017-05-06 | 26 |  | Critical |  |  | 2 | 2 | 2 | 4 | 0 | 8
|  |  |  | High |  |  | 2
|  |  |  | Medium |  |  | 4
9 | 2017-05-08 | 28 |  | Critical | 1 |  | 5 | 6 | 6 | 5 | 7 | 10
|  |  |  | High | 1 | 2 | 3
|  |  |  | Medium | 3 |  | 2
Suggestions |  |  |  |  | In-Progress Statuses |  | Closed Statuses | Total
[5 empty] | Active | Resolved | Closed